Statement of Work

Risk Data and Compliance Analytics Platform — James and Sons

| Field | Value |
| --- | --- |
| SOW Number | SOW-2024-1478 |
| Parent MSA | MSA-2023-1478 |
| Supplier | James and Sons |
| Supplier ID | S00007 |
| McKesson Cost Center | CC-7630 — Compliance |
| Category | Data & Compliance Services |
| SOW Effective Date | January 1, 2024 |
| SOW Expiration Date | December 31, 2024 |
| Not-to-Exceed (NTE) Amount | $890,000 USD |
| Ariba Contract ID | ARIBA-2024-SOW-2024-1478 |

1. Scope of Work

James and Sons shall provide Risk & Compliance Data services to McKesson Corporation as described in this Statement of Work. Any work outside this scope requires a written Change Order.

1.1  In-Scope Activities

- Access to third-party risk intelligence platform for supplier and third-party risk screening

- Batch screening of McKesson supplier base (up to 5,000 records)

- Adverse media monitoring for tier-1 suppliers

- API integration support with McKesson's GRC system

1.2  Explicitly Out of Scope

- Consumer credit reporting

- Legal research (governed under Bloomberg SOW)

- OFAC compliance (owned by McKesson Legal)

2. Approved Cost Categories

| GL Code | Category | Cap / Notes |
| --- | --- | --- |
| 7630-001 | Platform Access — Annual License | SaaS subscription |
| 7630-002 | Batch Screening Services | Per 1,000 records |
| 7630-003 | API Integration Professional Services | One-time; capped at $80,000 |

3. Deliverables and Milestones

| Deliverable | Due Date | Value | Condition |
| --- | --- | --- | --- |
| Platform go-live | February 28, 2024 | $220,000 | API integration acceptance |
| Q2 screening run | June 30, 2024 | $180,000 | Batch completion |
| Q4 screening run | November 30, 2024 | $180,000 | Batch completion |
| Annual license renewal | December 31, 2024 | $310,000 | Auto-renewal |

4. Billing and Invoice Instructions

4.1  All invoices must reference SOW SOW-2024-1478 and the applicable Ariba Contract ID.

4.2  Monthly T&M invoices must attach approved timesheets or task completion evidence.

4.3  Milestone payments will be released within 10 business days of written McKesson acceptance.