Statement of Work

Distribution Center Automation — Phase 3 — Jackson-Cortez

| Field | Value |
| --- | --- |
| SOW Number | SOW-2024-2034 |
| Parent MSA | MSA-2023-2034 |
| Supplier | Jackson-Cortez |
| Supplier ID | S00011 |
| McKesson Cost Center | CC-7710 — Distribution Operations |
| Category | Automation & Logistics Solutions |
| SOW Effective Date | January 1, 2024 |
| SOW Expiration Date | December 31, 2024 |
| Not-to-Exceed (NTE) Amount | $2,100,000 USD |
| Ariba Contract ID | ARIBA-2024-SOW-2024-2034 |

1. Scope of Work

Jackson-Cortez shall provide Warehouse Automation services to McKesson Corporation as described in this Statement of Work. Any work outside this scope requires a written Change Order.

1.1  In-Scope Activities

- Design and implementation of conveyor and sortation upgrades at McKesson Memphis DC

- System integration with McKesson WMS

- Factory acceptance testing and site acceptance testing

- 12-month warranty support post go-live

1.2  Explicitly Out of Scope

- Civil or structural construction

- IT network infrastructure

- Operator training beyond 5 days initial training

2. Approved Cost Categories

| GL Code | Category | Cap / Notes |
| --- | --- | --- |
| 7710-001 | Engineering and Design | Phase 1 design fees |
| 7710-002 | Equipment and Installation | Automation hardware and labor |
| 7710-003 | Integration and Testing | WMS integration and UAT |
| 7710-004 | Warranty Support | 12-month post go-live |

3. Deliverables and Milestones

| Deliverable | Due Date | Value | Condition |
| --- | --- | --- | --- |
| Design complete | March 31, 2024 | $280,000 | McKesson sign-off |
| Equipment delivery | June 30, 2024 | $600,000 | Goods receipt |
| Installation complete | September 30, 2024 | $700,000 | SAT pass |
| Go-live | November 30, 2024 | $520,000 | UAT acceptance |

4. Billing and Invoice Instructions

4.1  All invoices must reference SOW SOW-2024-2034 and the applicable Ariba Contract ID.

4.2  Monthly T&M invoices must attach approved timesheets or task completion evidence.

4.3  Milestone payments will be released within 10 business days of written McKesson acceptance.