Statement of Work

SAP Track & Trace Implementation — White-Preston

| Field | Value |
| --- | --- |
| SOW Number | SOW-2024-2589 |
| Parent MSA | MSA-2023-2589 |
| Supplier | White-Preston |
| Supplier ID | S00012 |
| McKesson Cost Center | CC-7425 — IT Operations |
| Category | Supply Chain Technology Services |
| SOW Effective Date | January 1, 2024 |
| SOW Expiration Date | December 31, 2024 |
| Not-to-Exceed (NTE) Amount | $540,000 USD |
| Ariba Contract ID | ARIBA-2024-SOW-2024-2589 |

1. Scope of Work

White-Preston shall provide SAP Track & Trace services to McKesson Corporation as described in this Statement of Work. Any work outside this scope requires a written Change Order.

1.1  In-Scope Activities

- SAP Advanced Track & Trace for Pharmaceuticals (ATTP) configuration and deployment

- Integration with McKesson SAP ERP and serialization systems

- User acceptance testing support

- Go-live hypercare (60 days post go-live)

1.2  Explicitly Out of Scope

- SAP licensing (procured separately)

- Hardware or infrastructure

- End-user training beyond 3 sessions

2. Approved Cost Categories

| GL Code | Category | Cap / Notes |
| --- | --- | --- |
| 7425-001 | SAP Implementation Services | Primary consulting |
| 7425-002 | Integration Services | ERP and serialization integration |
| 7425-099 | Reimbursable Expenses | Travel; capped at $18,000 |

3. Deliverables and Milestones

| Deliverable | Due Date | Value | Condition |
| --- | --- | --- | --- |
| Blueprint complete | March 15, 2024 | $110,000 | Acceptance |
| Config and build | June 30, 2024 | $160,000 | UAT pass |
| Go-live | September 30, 2024 | $160,000 | Go-live sign-off |
| Hypercare close | November 30, 2024 | $110,000 | Acceptance |

4. Billing and Invoice Instructions

4.1  All invoices must reference SOW SOW-2024-2589 and the applicable Ariba Contract ID.

4.2  Monthly T&M invoices must attach approved timesheets or task completion evidence.

4.3  Milestone payments will be released within 10 business days of written McKesson acceptance.