Statement of Work

Healthcare Market Strategy Consulting — May, Henry and Jackson

| Field | Value |
| --- | --- |
| SOW Number | SOW-2024-2923 |
| Parent MSA | MSA-2023-2923 |
| Supplier | May, Henry and Jackson |
| Supplier ID | S00010 |
| McKesson Cost Center | CC-7620 — Corporate Strategy |
| Category | Business Process Services |
| SOW Effective Date | January 1, 2024 |
| SOW Expiration Date | December 31, 2024 |
| Not-to-Exceed (NTE) Amount | $360,000 USD |
| Ariba Contract ID | ARIBA-2024-SOW-2024-2923 |

1. Scope of Work

May, Henry and Jackson shall provide Healthcare Consulting services to McKesson Corporation as described in this Statement of Work. Any work outside this scope requires a written Change Order.

1.1  In-Scope Activities

- Strategic advisory for McKesson's Pharmaceutical Distribution segment

- Market entry analysis for two target segments

- Competitive landscape assessment

- Executive presentation support

1.2  Explicitly Out of Scope

- Financial modelling or investment banking services

- Regulatory filings

- Lobbying

2. Approved Cost Categories

| GL Code | Category | Cap / Notes |
| --- | --- | --- |
| 7620-001 | Strategy Consulting | Primary advisory |
| 7620-099 | Reimbursable Expenses | Travel; capped at $12,000 |

3. Deliverables and Milestones

| Deliverable | Due Date | Value | Condition |
| --- | --- | --- | --- |
| Market analysis report | April 30, 2024 | $100,000 | Acceptance |
| Strategy recommendations | July 31, 2024 | $120,000 | Acceptance |
| Final executive presentation | October 31, 2024 | $140,000 | Acceptance |

4. Billing and Invoice Instructions

4.1  All invoices must reference SOW SOW-2024-2923 and the applicable Ariba Contract ID.

4.2  Monthly T&M invoices must attach approved timesheets or task completion evidence.

4.3  Milestone payments will be released within 10 business days of written McKesson acceptance.