Statement of Work

Leadership Coaching and Development Program — May, Henry and Jackson

| Field | Value |
| --- | --- |
| SOW Number | SOW-2024-3145 |
| Parent MSA | MSA-2023-3145 |
| Supplier | May, Henry and Jackson |
| Supplier ID | S00010 |
| McKesson Cost Center | CC-7650 — HR & Talent |
| Category | Business Process Services |
| SOW Effective Date | January 1, 2024 |
| SOW Expiration Date | December 31, 2024 |
| Not-to-Exceed (NTE) Amount | $240,000 USD |
| Ariba Contract ID | ARIBA-2024-SOW-2024-3145 |

1. Scope of Work

May, Henry and Jackson shall provide Leadership Development services to McKesson Corporation as described in this Statement of Work. Any work outside this scope requires a written Change Order.

1.1  In-Scope Activities

- Executive coaching for 15 identified senior leaders (6 sessions each)

- Leadership team offsites (2 sessions)

- 360-degree assessment and debrief support

1.2  Explicitly Out of Scope

- Recruitment or selection services

- Learning management system services

- Group training programs beyond offsites

2. Approved Cost Categories

| GL Code | Category | Cap / Notes |
| --- | --- | --- |
| 7650-001 | Executive Coaching | Per session |
| 7650-002 | Leadership Offsites | Facilitation fees |
| 7650-099 | Expenses | Travel; capped at $8,000 |

3. Deliverables and Milestones

| Deliverable | Due Date | Value | Condition |
| --- | --- | --- | --- |
| Cohort 1 coaching (Q1-Q2) | June 30, 2024 | $100,000 | Completion log |
| Cohort 2 coaching (Q3-Q4) | December 15, 2024 | $100,000 | Completion log |
| Offsites | Per event | $40,000 | Post-event acceptance |

4. Billing and Invoice Instructions

4.1  All invoices must reference SOW SOW-2024-3145 and the applicable Ariba Contract ID.

4.2  Monthly T&M invoices must attach approved timesheets or task completion evidence.

4.3  Milestone payments will be released within 10 business days of written McKesson acceptance.